## UTS Status_12052021
Issue Type | Key | Summary | Name of TP | SLA Status on JIRA | HPLM Ref No | Status | Ageing of ticket/email | ALM Status | Time to resolution | Severity | Environment | Created date/Reassignment date(which ever is Latest) | Current Date
Service Request | SR-1173 | Issues on UIT-B Environment (SMKI_AVAIL_CRL_ARL) | UWH | Not Breached |  | Pending |  |  | 31h |  | UIT - A |  | 2021-05-14
Service Request | SR-1155 | General Enquiries UWH UTRN | Ecotricity | Not Breached |  | Pending |  |  | 221h 40m |  | UIT - A |  | 2021-05-14
Service Request | SR-1147 | Config Test PAYG Meter Set-UIT A | EON | Not Breached |  | Work in progress | 8 |  | 213h 53m |  | UIT - A | 2021-05-06 | 2021-05-14
Service Request | SR-1144 | EON: MDUST - Secure - Negative Scenario test | EON | Not Breached |  | Pending |  |  | 224h 16m |  | UIT - B |  | 2021-05-14
Service Request | SR-1138 | UTS: EON: Request for Secure DF meter set with Chameleon IHD | EDF | Not Breached |  | Pending |  |  | 227h 52m |  | UIT |  | 2021-05-14
Service Request | SR-1132 | EDF - Device Logs Requirement. | Utilita | Not Breached |  | Pending |  |  | 237h 30m |  | UIT - A |  | 2021-05-14
Service Request | SR-1091 | Utilita Plan ¦ MDUST | EON | Not Breached |  | Pending |  |  | 188h 33m |  | UIT - A |  | 2021-05-14
Service Request | SR-1075 | Decommissioned SMETS1 device which is enrolled and registered in UIT-A can be recommissioned. | EGAS | Not Breached |  | Pending |  |  | 232h 2m |  | UIT - A |  | 2021-05-14
Service Request | SR-1071 | DM Update Request -EGAS ¦ SMETS1 ¦ UIT A ¦ DUST | EGAS | Not Breached |  | Pending |  |  | 250h |  | UIT - B |  | 2021-05-14
Service Request | SR-1070 | DM Update Request -EGAS ¦ SMETS1 ¦ UIT A ¦ MDUST | EDF | Not Breached |  | Pending |  |  | 250h |  | UIT - B |  | 2021-05-14
Defect UIT | SDM-106 | EDF E2E: SMETS1 DCC Lab : Secure GSME: GEO TRIO 2 PPMID Does not display Debt Recovery rate for GSME | CGI | Not Breached | 201296 | Pending | - | Assigned to DCC | 146h 37m | S2-High | UIT - A |  | 2021-05-14
Defect UIT | SDM-104 | CGI-UTS SMETS1 MOC Monitoring UIT B - All MOC Service Requests Timed Out | EON | Not Breached | 201276 | Pending | - | Assigned to DCC | 306h | S3-Medium | UIT - A |  | 2021-05-14
Defect UIT | SDM-103 | Additonal data(MPXN and device details) in S1MIG -02 is captured when MPXN was not sent on MAF | EON | Not Breached | 201257 | Pending | - | Assigned to DCC | 300h 50m | S3-Medium | UIT - A |  | 2021-05-14
Defect UIT | SDM-101 | On ESME EC was not activated but EC balance is consumed and post Friendly hours meter was not dissconect when meter balance is negative | EON | Not Breached | 201245 | Pending | - | Assigned to DCC | 250h 34m | S3-Medium | UIT - A |  | 2021-05-14
Defect UIT | SDM-100 | Secure GSME - Behaviour of ADR and EC balance when there is no CREDIT on meter during friendly hours. | EON | Not Breached | 201252 | Pending | - | Assigned to DCC | 284h 56m | S3-Medium | UIT - B |  | 2021-05-14
Defect UIT | SDM-99 | How does Secure meter ESME or GSME behave when Meter has 0 credit and EC balance(full balance) of 5 pounds on Friday evening(friendly hours ) and EC not activated. | British Gas | Not Breached | 201251 | Pending | - | Assigned to DCC | 275h 47m | S3-Medium | UIT - B |  | 2021-05-14
Defect UIT | SDM-97 | SMETS 1_MOC_Secure GSME_Emergency credit did not reset to expected value on back of SR 3.2 and SR 1.6 PP-PP | British Gas | Not Breached | 201243 | Pending | - | Assigned to DCC | 143h 35m | S2-High | UIT - A |  | 2021-05-14
Defect UIT | SDM-96 | SMETS 1_MOC_Secure ESME_Emergency credit did not reset to expected value on back of SR 3.2 and SR 1.6 PP-PP | EON | Not Breached | 201242 | Pending | - | Assigned to DCC | 143h 29m | S2-High | UIT - A |  | 2021-05-14
Defect UIT | SDM-94 | ESME Debt register values are not correctly populated on 4.3 response | Telecoms Plus | Not Breached | 201234 | Pending | - | Assigned to DCC | 96h 27m | S3-Medium | UIT - A |  | 2021-05-14
Defect UIT | SDM-91 | SMETS1 MOC:UIT-A:8.11 failing with E21 error during Join process of backward compatible PPMID to ESME SMETS1 | EON | Not Breached | 201218 | Pending | - | Assigned to DCC | 288h 53m | S3-Medium | UIT - A |  | 2021-05-14
Defect UIT | SDM-88 | EON - H-EONE-076-UA - Secure GSME - Debit register values are not correctly populated on the 4.3 XML | Octopus Energy | Not Breached | 201214 | Pending | - | Assigned to DCC | 54h 9m | S3-Medium | UIT - B |  | 2021-05-14
Defect UIT | SDM-78 | Octopus DUST - H-OCTO-008-UA (Secure) - Scheduled 4.6.1 to GPF -N11 - GSME_Profile and Daily reads are not generated for the Migrated S1 Customers | CGI | Not Breached | 201117 | Pending | - | Assigned to DCC | 168h 39m | S3-Medium | UIT - B |  | 2021-05-14
Defect UIT | SDM-69 | Core1.2 - UIT-B - Set H-CGIS-1075-UB: CGI-A SR11.1 Secure PPMID OTA gets 8F1C Failure | British Gas | Not Breached | 201014 | Pending | - | Assigned to DCC | 198h 53m | S3-Medium | UIT - A |  | 2021-05-14
Defect UIT | SDM-47 | UTS @ DUST @ BG_DUST_Secure GSME/GPF_SR 4.1.1 and SR 4.1.2 triggered as part of ODR takes 30 minutes of wake-up cycle to respond | - | Not Breached | 200851 | Pending | - | Assigned to DCC | 140h 8m | S4-Low | UIT - A |  | 2021-05-14